## Gantt Chart Template
GANTT CHART |  |  |  | https://goo.gl/PXLbMe
| PROJECT TITLE | Quadraped Robot For Smart Agriculture
| LAST UPDATED | 2025-01-28
|  |  | FULL PROTOTYPE | [8 empty] | PRESENTATION
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | Febuary |  |  |  | March |  |  |  |  | April
|  |  | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 17 | 24
| Power system test | 0% | bar: March 3
| Walking software | 30% | bar: Febuary 3 to Febuary 17
| Basic motion acheived | 0% | bar: Febuary 17
| Build full prototype | 60% | bar: Febuary 3 to Febuary 10
| 2 Legs complete | 95%
| 90% of body complete | 100%
| All legs mounted and wired | 25% | bar: Febuary 17
| Body complete with lid | 20% | bar: Febuary 17
| Flat Terrain Testing, Debugging | 0% | bar: Febuary 10 to March 3
| Walks with no tether | 0% | bar: March 17
| All design requirements fulfilled | 10% | bar: March 31
| All deliverables delivered | 0% | bar: April 7
Presentation
presentation board | bar: March 17 to April 7
prep for design day | bar: April 7 to April 14
Design Day | bar: April 17

## Getting Moving
GANTT CHART | [22 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Quadraped Robot For Smart Agriculture
| LAST UPDATED | 2024-10-26
|  |  |  | DESIGN CONCEPT | [13 empty] | FULL PROTOTYPE | [12 empty] | PRESENTATION
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | TEAM MEMBERS | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April
|  |  |  | 1 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 17 | 24
Walking Software/Prototype | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
| Build Test Stand | 100 | bar: October 28 to November 4
| Code IMU control | 20% | bar: November 4 to November 18
| Build Single Leg Test Stand | 100% | bar: November 25 to December 9
Code Leg Control | bar: December 9 to January 13
Build Legs | bar: January 6 to January 20
Build Body | bar: January 13 to January 27
Refine leg control for full body | bar: January 20 to January 27
Leg Control Code | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
Stabilize according to IMU | bar: January 27 to Febuary 3
Basic forward motion
Design simple Forward Gait | bar: Febuary 3 to Febuary 10
Implement Turning | bar: Febuary 10 to Febuary 17
Refine gait to work with all legs
Stand and Sit primitives | bar: January 27 to Febuary 3