## Gantt Chart Template
GANTT CHART | [22 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Quadraped Robot For Smart Agriculture
| LAST UPDATED | 2024-10-26
|  |  |  | DESIGN CONCEPT | [13 empty] | FULL PROTOTYPE | [12 empty] | PRESENTATION
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | TEAM MEMBERS | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April
|  |  |  | 1 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 17 | 24
Design Concept Work | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
| Everything Ordered (Except drivers, power system) | 100% | Yang | bar: October 21
| Milestones/Gantt Chart Review | 100% | All | bar: October 28
| Part Arrival | 90% | All | bar: October 14 to November 4; November 25; January 13 to January 20
| Test Rig Design | 100% | Ben, Yang, Austin | bar: October 28 to November 4
| Test Rig Assembly | 100% | Ben, Yang, Austin | bar: November 4 to November 11
| Prepare Orange Pi/Design Control Software | 90% | Kevin, Sam, Jordan | bar: November 25 to December 2
| Decide on and order full set of drivers | 100% | All | bar: November 18
| Build Driver communication software | 90% | Kevin, Sam, Jordan | bar: November 11 to December 2
| Execute/Present Test | 80% | All | bar: December 2 to December 9
Full Prototype | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
| Walking software | 10% | bar: December 2 to January 20
| Build full prototype | 0% | bar: January 6 to January 20
| beacon navigation software | 0% | bar: January 27 to Febuary 10
| Design Power System | 80% | bar: November 18 to December 2
| Order Power System | 50% | bar: December 9
| Flat Terrain Testing, Debugging | 0% | All | bar: January 27 to Febuary 10
| Rough Terrain Testing, Debugging | 0% | All | bar: Febuary 17 to March 3
| All design requirements fulfilled | 10% | All | bar: March 3
presentation board | bar: March 17 to April 7
prep for design day | bar: April 7 to April 14
Design Day | bar: April 17

## Getting Moving
GANTT CHART | [22 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Quadraped Robot For Smart Agriculture
| LAST UPDATED | 2024-10-26
|  |  |  | DESIGN CONCEPT | [13 empty] | FULL PROTOTYPE | [12 empty] | PRESENTATION
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | TEAM MEMBERS | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April
|  |  |  | 1 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 17 | 24
Walking Software/Prototype | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
| Build Test Stand | 100 | bar: October 28 to November 4
| Code IMU control | 20% | bar: November 4 to November 18
| Build Single Leg Test Stand | 70% | bar: November 25 to December 9
Code Leg Control | bar: November 25 to December 30
Build Full Prototype Body, Legs | bar: January 6 to January 20
Refine leg control for full body | bar: January 6 to January 20
Leg Control Code | bar: October 1; October 14 to December 9; January 6 to March 3; March 17 to April 24
Stabilize according to IMU | bar: November 25 to December 2
Basic forward motion | bar: December 9 to December 16
Design simple Forward Gait | bar: December 23 to December 30
Implement Turning | bar: January 6 to January 20
Refine gait to work with all legs | bar: January 6 to January 20